## Sheet1
No	Period	Task	Result	Res	1	2	3	4	5	6	7	8	9	10	11	12
1	PLAN(1-4)	Group Name and Membership	Project Membership structure map	/
2	PLAN	Roles of everyone in the group[algorithms, i/o, testing]	Project Membership structure map	/
3	PLAN	Describe the key mathematical steps in easy-to-understand terms	3-5 pages slides handcraft	Tan
4	PLAN	Show how that leads to a flow diagram of the implementation	flow chart of implementation	Li
5	PLAN	Present a plan showing the core algorithmic functions and who will implement them. Stage the development .	Development plan	Tan
6	PLAN	Define an e2e test and how it will be implemented	E2E test instances list	Gong
7	PLAN	Define unit tests for your core functionality	unit test instances list	Gong
8	PLAN	Declare some milestones and timeline	This plan	Li
		Slides integration	Plan slides	Gong				★
9	MATLAB IMP(5-6)	Implement Core Algorithm function block	Functional Code block	Tan
10		Integrate the code and compare the result with Laplacian matting	Matlab Project	Li
11		Code Linting and review	Matlab Project	Li
12		Unit Test and e2e test	Test Report	Gong						★
13	PYTHON IMP & PROGRESS UPDATE(7-9)	Implement Core Algorithm function block	Functional Code block	Tan
14		Integrate the code	Python Project	Li
15		Code Linting and review	Python Project	Li
16		Unit Test and e2e test	Test Report	Gong
17		Slides update Algo	3 pages slides	Tan
18		Slides update Inte	3 pages slides	Li
19		Slides update Test	3 pages slides	Gong									★
20	FINAL PRESENTATION(10-11)	Slides update Algo	5 pages slides	Tan
21		Slides update Inte	5 pages slides	Li
22		Slides update Test	5 pages slides	Gong
23	TEST OTHER CODE(12)	Lint check	Lint Report	Li
24		Unit Test	Unit test Report	Tan
25		E2E Test	E2E test report	Gong
26		Test Report	Integrated Test Report	Li												★